## Budget_Example
Instructions: To add or delete columns, go into the budget table below, insert/delete "cells" instead of "columns" from top of page; or cut first five rows, add your columns, and insert first five rows back into the top of the form. | [8 empty] | MPCA Use Only
Project title: | [8 empty] | Swift #:
| [No more than 10 words, 50 characters or less] [For watershed program work, use watershed name and project type (e.g., Snake River Watershed Restoration and Protection Project)] | [7 empty] | CR #:
| 1. Personnel |  |  |  | 2. Subcontracting | 3. Equipment |  | 4. Other Expenses |  |  | Totals (Extended)
Project Budget | Project Manager | Water Plan Technician | Hydrologist | Modeler | Laboratory Analysis | Coolers | YSI meter | Mileage | Shipping | Printing
$ Rate per Hour/Unit | 110 | 45 | 127 | 130 |  |  |  | 0.55
Objective 1
Task A | 24 |  | 20 | 10 |  |  |  | 51
Sub-task 1
Sub-task 2
Task B | 10 |  | 10 | 10
Sub-task 1
Sub-task 2
Task C | 5 |  | 5 | 10
Total for Objective 1 Hrs | 39 | 0 | 35 | 30
Total for Objective 1 $ | 4290 | 0 | 4445 | 3900 | 0 | 0 | 0 | 51 | 0 | 0 | 12686
Objective 2
Task A | 2 | 20 | [5 empty] | 76.5
Task B | 6 | 6 | 10 | 15 | 1500 | 60 | 350 | 76.5 | 150
Task C | 2 | 2
Total for Objective 2 Hrs | 10 | 28 | 10 | 15
Total for Objective 2 $ | 1100 | 1260 | 1270 | 1950 | 1500 | 60 | 350 | 153 | 150 | 0 | 7793
Objective 3
Task A | 5 | 2 | [5 empty] | 25.5 |  | 250
Task B | 6 | 2 | [5 empty] | 25.5
Total for Objective 3 Hrs | 11 | 4 | 0 | 0
Total for Objective 3 $ | 1210 | 180 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 250 | 1691
Total Project Hours | 60 | 32 | 45 | 45
Total Budget Per Objective: | 6600 | 1440 | 5715 | 5850 | 1500 | 60 | 350 | 255 | 150 | 250 | 22170
Laboratory analyses:
Objective 2:
Total Phosphorus 25 x $11 |  |  | 275
Chlorophyll-a 25 x $20 |  |  | 500
E.coli 29 samples x $25 |  |  | 725
|  | Total | 1500
Attachment A Project Budget Doc Type: Contract
Attachment A Project Budget Doc Type: Contract
Attachment A Project Budget Doc Type: Contract
Attachment A Project Budget Doc Type: Contract

## Gantt template
MPCA Use Only
| Project title: | [24 empty] | SWIFT #
|  | [No more than 10 words, 50 characters or less] [For watershed program work, use watershed name and project type (e.g., Snake River Watershed Restoration and Protection Project)] | [23 empty] | CR #
[6 empty] | Year |  | 20__ | [9 empty] | Year |  | 20__ | [9 empty] | Year |  | 20__
|  | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Objective 1:
Task A
Task B
Task C
Objective 1 Deliverables Due
Objective 2:
Task A
Task B
Task C
Objective 2 Deliverables Due
Objective 3:
Task A
Task B
Objective 3 Deliverables Due
Attachment A Gantt Chart Doc Type: Contract