## Gantt Chart
CWP Project Gantt Chart
CWP Project Budget and Expenditure Report
Clean Water Partnership (CWP) Program
Doc Type: Semi-annual Report
PROJECT NAME:
[6 empty] | Year 2012 | [11 empty] | Year 2013 | [11 empty] | Year 2014
|  | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
OBJECTIVE A: WATERSHED INFORMATION AND EDUCATION
Task 1 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X
Task 2 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Task 3 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Task 4 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Task 5 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Task 6 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Reports Due | [14 empty] | X | [5 empty] | X | [5 empty] | X | [5 empty] | X | bar: Year 2012 A
Timeline: January 2012 to April 2014
OBJECTIVE B: EDUCATIONAL DEMONSTRATIONS
Task 1 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X
Task 2 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X
Timeline: January 2013 to November 2013
OBJECTIVE C: ON-SITE WASTEWATER MANAGEMENT
Task 1 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: Year 2012 M to Year 2012 D
Task 2 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: Year 2012 M to Year 2012 D
Task 3 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: Year 2012 M to Year 2012 D
Timeline: May 2012 to April 2014
OBJECTIVE D: WATER QUALITY MONITORING
Task 1 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: Year 2012 M to Year 2012 D
Task 2 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: Year 2012 M to Year 2012 D
Task 3 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: Year 2012 M to Year 2012 D
Data Due | [24 empty] | X | [11 empty] | X | bar: Year 2012 D
Timeline: March 2012 to April 2014
OBJECTIVE E: BMP EVALUATION AND ADJUSTMENT
Task 1 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: Year 2012 M to Year 2012 D
Task 2 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: Year 2012 M to Year 2012 D
Task 3 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: Year 2012 M to Year 2012 D
Task 4 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: Year 2012 M to Year 2012 D
Task 5 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: Year 2012 M to Year 2012 D
Task 6 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: Year 2012 M to Year 2012 D
Task 7 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: Year 2012 M to Year 2012 D
Timeline: Conduct work on a routine basis as specified in the above Action statements.
OBJECTIVE F: MANAGEMENT AND ADMINISTRATION OF PROJECT
Task 1 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Task 2 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Task 3 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Task 4 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Task 5 | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Timeline: January 2013 to April 2014

## Budget-Expenses1
CWP Project Budget-Expenses 1
CWP Project Budget and Expenditure Report
Clean Water Partnership (CWP) Program
Doc Type: Semi-annual Report
| Project Name: | [8 empty] | Period ending:
[9 empty] | I. |  |  | II. | III.A. | III.B. | III.C. | III.D. | III.E. | III.F. | III.G. | III.H. | iV. | V.
|  |  |  | Quantity | [8 empty] | Year 1 | Year 1 | Year 2 | Year 2 | Year 3 | Year 3 | Year 4 | Year 4 | Cumulative | Budget
| Cost Category | Unit |  | (Hours/Amount) |  |  |  | Subtotals | Match | Loan | Grant | Total | Jan 1 - Jun 30 | Jul 1 - Dec 31 | Jan 1 - Jun 30 | Jul 1 - Dec 31 | Jan 1 - Jun 30 | Jul 1 - Dec 31 | Jan 1 - Jun 30 | Jul 1 - Dec 31 | Expend. | Balance
|  | Cost |  | Exp./Budget |  |  |  | In-Kind | Cash | Funds | Cash | Budget | Expended | Expended | Expended | Expended | Expended | Expended | Expended | Expended | (III.A. thr H.) | (IV - II)
OBJECTIVE 1 - DEVELOPMENT OF PROJECT WORKPLAN
A) Contributing Sponsors
DNR
| Project Manager | 20 | /hr. | 0 | / | 700 | hrs. | 14000 |  |  |  | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000
| Hydrologist | 25 | /hr. | 0 | / | 100 | hrs. | 2500 |  |  |  | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
| Administration | [7 empty] | 500 |  |  | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500
| Transportation | [7 empty] | 500 |  |  | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500
SWCD
| Secretary | 15 | /hr. | 0 | / | 15 | hrs. | 225 |  |  |  | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225
Supplies
| Cmptr. Disk | 1 | /unit |  | / | 15 | units | 200 |  |  |  | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200
Subtotal - Acme Consultants | Postage | 0 | [6 empty] | 500 |  |  | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500
| Misc. Office | 0 | [5 empty] | 300 | 5000 |  |  | 5300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5300
| Volunteer Sup. | 0 | [6 empty] | 5000 |  |  | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
B) Project Sponsor | Aerial Imagery | 0 | [6 empty] | 12000 |  |  | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
| OBJECTIVE 1 - TOTAL | [6 empty] | 17225 | 23500 | 0 | 0 | 40725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40725
OBJECTIVE 2 - LAKE WATER QUALITY MONITORING
A) Contributing Sponsors
DNR
| Project Manager | 20 | /hr. | 0 | / | 200 | hrs. | 4000 |  |  |  | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
| Administration | 0 | [6 empty] | 1000 |  |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
| Transportation | 0 | [6 empty] | 2000 |  |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
| Hydrologist | 25 | /hr. | 0 | / | 400 | hrs. | 10000 |  |  |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
| Materials | 0 | [5 empty] | 2000 |  |  |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
| Gas & Lodging | 0 | [5 empty] | 2000 |  |  |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
| Data Analysis | 0 | [5 empty] | 2000 |  |  |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
SWCD
| Dist. Manager | 19 | /hr. | 0 | / | 10 | hrs. | 190 |  |  |  | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190
| Technician | 12 | /hr. | 0 | / | 160 | hrs. |  | 1920 |  |  | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920
| Secretary | 15 | /hr. | 0 | / | 20 | hrs. | 300 |  |  |  | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300
| Area Volunteers | 12 | /hr. | 0 | / | 50 | hrs. | 600 |  |  |  | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600
Subtotal - Acme Consultants | Analysis | 0 | [7 empty] | 2000 | 2000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
Army COE
| District Ranger | 25 | /hr. | 0 | / | 48 | hrs. | 1200 |  |  |  | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200
| SUBTOTAL | [6 empty] | 22290 | 4920 | 2000 | 2000 | 31210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31210
B) Project Sponsor | USCOE Lab Parameters (Lake)
| Water Qual. Anal. | 0 | [5 empty] | 1212 |  |  |  | 1212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212
| 10% contingency | 0 | [5 empty] | 121 |  |  |  | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121
| QA/QC (15%) | 0 | [5 empty] | 182 |  |  |  | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182
| SUBTOTAL | [6 empty] | 1515 |  |  |  | 1515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515
C) | DNR Fisheries
| Fish Survey | 0 | [5 empty] | 34300 |  |  |  | 34300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34300
D) | USCOE
| Core Sampling | 200 |  |  |  | 12 |  | 2400 |  |  |  | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400
| OBJECTIVE 2 - TOTAL | [6 empty] | 60505 | 4920 | 2000 | 2000 | 69425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69425
OBJECTIVE 3 - STREAM WATER QUALITY MONITORING
A) Contributing Sponsors
DNR
| Project Manager | 20 | /hr. | 0 | / | 500 | hrs. | 10000 |  |  |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
| Administration | 0 | [6 empty] | 1000 |  |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
| Transportation | 0 | [6 empty] | 2000 |  |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
| Hydrologist | 25 | /hr. | 0 | / | 480 | hrs. | 12000 |  |  |  | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
| Materials | 0 | [5 empty] | 2000 |  |  |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
| Gas & Lodging | 0 | [5 empty] | 4500 |  |  |  | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
| Data Analysis | 0 | [5 empty] | 4000 |  |  |  | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
SWCD
| Dist. Manager | 19 | /hr. | 0 | / | 20 | hrs. | 380 |  |  |  | 380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380
| Technician | 12 | /hr. | 0 | / | 320 | hrs. |  | 3840 |  |  | 3840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3840
| Secretary | 15 | /hr. | 0 | / | 10 | hrs. | 150 |  |  |  | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150
| Area Volunteers | 12 | /hr. | 0 | / | 50 | hrs. | 600 |  |  |  | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600
Subtotal - Acme Consultants | Analysis | 0 | [8 empty] | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
(ACOE)
| Equipment | 0 | [5 empty] | 2500 |  |  | 29262 | 31762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31762
| Consulting | 0 | [8 empty] | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
| SUBTOTAL | [6 empty] | 36130 | 6840 | 0 | 37262 | 80232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80232
B) Project Sponsor | Lab Parameters (stream)
| Water Qual. Anal. | 0 | [6 empty] | 12506 |  |  | 12506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12506
| 10% contingency | 0 | [6 empty] | 1251 |  |  | 1251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1251
| QA/QC (15%) | 0 | [6 empty] | 1876 |  |  | 1876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1876
| Shipping | 0 | [6 empty] | 1000 |  |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
| SUBTOTAL | [6 empty] | 0 | 16633 |  |  | 16633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16633
C) | Mussel Biomonitoring
| Equipment | 0 | [7 empty] | 5000 | 1300 | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6300
| U of M (F & W) | 20 | /hr. | 0 | / | 150 | hrs. |  | 3000 |  |  | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
| Gas & Lodging | 0 | [6 empty] | 1000 |  |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
| SUBTOTAL | [6 empty] | 0 | 4000 |  |  | 10300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10300
| OBJECTIVE 3 - TOTAL | [6 empty] | 36130 | 27473 | 5000 | 38562 | 107165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107165
OBJECTIVE 4 - WATERSHED ASSESSMENT
A) Contributing Sponsors
DNR
| Project Manager | 20 | /hr. | 0 | / | 773 | hrs. | 15460 |  |  |  | 15460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15460
| Administration | 0 | [6 empty] | 1000 |  |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
| Transportation | 0 | [6 empty] | 2000 |  |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
SWCD
| Dist. Manager | 20 | /hr. | 0 | / | 300 | hrs. | 6000 |  |  |  | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
| Technician | 12 | /hr. | 0 | / | 100 | hrs. |  | 1200 |  |  | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200
| Secretary | 15 | /hr. | 0 | / | 40 | hrs. | 600 |  |  |  | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600
| Suppl/Software | 0 | [6 empty] | 8292 |  | 708 | 8292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8292
| area volunteers | 12 | /hr | 0 | / | 0 | hrs |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| OBJECTIVE 4 - TOTAL | [6 empty] | 22060 | 12492 | 0 | 708 | 34552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34552
OBJECTIVE 5 - IDENTIFICATION OF BEST MANAGEMENT PRACTICES
DNR
| Project Manager | 20 | /hr. | 0 | / | 303 | hrs. | 6060 |  |  |  | 6060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6060
| Administration | 0 | [6 empty] | 1000 |  |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
| Transportation | 0 | [6 empty] | 2000 |  |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
SWCD
| Dist. Manager | 19 | /hr. | 0 | / | 200 | hrs. | 3800 |  |  |  | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800
| Secretary | 15 | /hr. | 0 | / | 40 | hrs. | 600 |  |  |  | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600
| Compliance Technician | 28 | /hr. |  |  | 2810 | hrs. |  | 78680 |  |  | 78680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78680
| Restoration | 0 | [6 empty] | 16000 |  |  | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000
| Misc. Office | 0 | [8 empty] | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
| Video Production | 0 | [8 empty] | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
| Newsletter, Brochure | 0 | [8 empty] | 5385 | 5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5385
| area volunteers | 12 | /hr | 0 | / | 0 | hrs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BMP activities | [8 empty] | 250000
| OBJECTIVE 5 - TOTAL | [6 empty] | 10460 | 97680 | 250000 | 22385 | 130525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130525
OBJECTIVE 6 - DATA ANALYSIS AND REPORT PREPARATION
DNR
| Project Manager | 20 | /hr. | 0 | / | 383 | hrs. | 7660 |  |  |  | 7660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7660
SWCD
| Dist. Manager | 19 | /hr. | 0 | / | 200 | hrs. | 3800 |  |  |  | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800
| Secretary | 15 | /hr. | 0 | / | 40 | hrs. | 600 |  |  |  | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600
| Technician | 12 | /hr. | 0 | / | 480 | hrs. |  | 5760 |  |  | 5760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5760
| Software | 0 | [8 empty] | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Misc. Office | 0 | [8 empty] | 2020 | 2020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020
| area volunteers | 12 | /hr | 0 | / | 0 | hrs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| OBJECTIVE 6 - TOTAL | [6 empty] | 12060 | 5760 | 0 | 3520 | 19840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19840
OBJECTIVE 7 - DEVELOPMENT OF IMPLEMENTATION PLAN
DNR
| Project Manager | 20 | /hr. | 0 | / | 553 | hrs. | 11060 |  |  |  | 11060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11060
| Administration | 0 | [6 empty] | 1500 |  |  | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
| hydrologist | 25 | /hr | 0 | / | 0 | hrs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SWCD
| Dist. Manager | 19 | /hr. | 0 | / | 200 | hrs. | 3800 |  |  |  | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800
| Secretary | 15 | /hr. | 0 | / | 40 | hrs. | 600 |  |  |  | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600
| Technician | 12 | /hr. | 0 | / | 200 | hrs. |  | 2400 |  |  | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400
| Misc. Office | 0 | [8 empty] | 2020 | 2020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020
| OBJECTIVE 7 - TOTAL | [6 empty] | 15460 | 3900 | 0 | 2020 | 21380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21380
ITEMIZED BUDGET
| OBJECTIVE 1 - TOTAL | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| OBJECTIVE 2 - TOTAL | [6 empty] | 60505 | 4920 | 2000 | 2000 | 69425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69425
| OBJECTIVE 3 - TOTAL | [6 empty] | 36130 | 27473 | 5000 | 38562 | 107165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107165
| OBJECTIVE 4 - TOTAL | [6 empty] | 22060 | 12492 | 0 | 708 | 34552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34552
| OBJECTIVE 5 - TOTAL | [6 empty] | 10460 | 97680 | 250000 | 22385 | 130525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130525
| OBJECTIVE 6 - TOTAL | [6 empty] | 12060 | 5760 | 0 | 3520 | 19840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19840
| OBJECTIVE 7 - TOTAL | [6 empty] | 15460 | 3900 | 0 | 2020 | 21380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21380
| G R A N D T O T A L | [6 empty] | 156675 | 152225 | 257000 | 69195 | 308900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308900

## Budget-Expenses2
CWP Project Budget-Expenses 2
CWP Project Budget and Expenditure Report
Clean Water Partnership (CWP) Program
Doc Type: Semi-annual Report
[PROJECT NAME] |  |  |  |  | II.A. | II.B. | II.C. | II.D. | II.E. | III.A.1. | III.A.2 | III.A.3. | III.A.4. | III.A.5. | III.B.1. | III.B.2 | III.B.3. | III.B.4. | III.B.5. | III.C.1. | III.C.2. | III.C.3. | III.C.4. | III.C.5. | III.D.1. | III.D.2 | III.D.3. | III.D.4. | III.D.5. | III.E.1. | III.E.2 | III.E.3. | III.E.4. | III.E.5. | III.F.1. | III.F.2 | III.F.3. | III.F.4. | III.F.5. | III.G.1. | III.G.2 | III.G.3. | III.G.4. | III.G.5. | III.H.1. | III.H.2 | III.H.3. | III.H.4. | III.H.5. | III.I.1. | III.I.2. | III.I.3. | III.I.4. | III.I.5. | IV.A. | IV.B. | IV.C. | IV.D. | IV.E. | V.A. | V.B | V.C. | V.D. | V.E.
[PROJECT SPONSOR] | [9 empty] | Year 1 | Year 1 | Year 1 | Year 1 | Year 1 | Year 1 | Year 1 | Year 1 | Year 1 | Year 1 | Year 2 | Year 2 | Year 2 | Year 2 | Year 2 | Year 2 | Year 2 | Year 2 | Year 2 | Year 2 | Year 3 | Year 3 | Year 3 | Year 3 | Year 3 | Year 3 | Year 3 | Year 3 | Year 3 | Year 3 | Year 4 | Year 4 | Year 4 | Year 4 | Year 4 | Year 4 | Year 4 | Year 4 | Year 4 | Year 4 | Year 5 | Year 5 | Year 5 | Year 5 | Year 5 | Cumulative | Cumulative | Cumulative | Cumulative | Cumulative | Budget Balance | Budget Balance | Budget Balance | Budget Balance | Budget Balance
ITEMIZED PROJECT BUDGET AND EXPENDITURES | [5 empty] | Cash | In-Kind | SRF | Budget | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jul 1 - Dec 31 | Jul 1 - Dec 31 | Jul 1 - Dec 31 | Jul 1 - Dec 31 | Jul 1 - Dec 31 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jul 1 - Dec 31 | Jul 1 - Dec 31 | Jul 1 - Dec 31 | Jul 1 - Dec 31 | Jul 1 - Dec 31 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jul 1 - Dec 31 | Jul 1 - Dec 31 | Jul 1 - Dec 31 | Jul 1 - Dec 31 | Jul 1 - Dec 31 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jul 1 - Dec 31 | Jul 1 - Dec 31 | Jul 1 - Dec 31 | Jul 1 - Dec 31 | Jul 1 - Dec 31 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Jan 1 - Jun 30 | Grant | Cash Match | In-kind | SRF Loan | Total Expended | Grant | Cash Match | In-kind | SRF Loan | Cumulative
Objective | Cost Category | Unit Cost | Rate | Quantity | Grant | Match | Match | Loan | Total | Grant Expended | Cash Match | In-kind Expended | SRF Expended | Total Expended | Grant Expended | Cash Match | In-kind Expended | SRF Expended | Total Expended | Grant Expended | Cash Match | In-kind Expended | SRF Expended | Total Expended | Grant Expended | Cash Match | In-kind Expended | SRF Expended | Total Expended | Grant Expended | Cash Match | In-kind Expended | SRF Expended | Total Expended | Grant Expended | Cash Match | In-kind Expended | SRF Expended | Total Expended | Grant Expended | Cash Match | In-kind Expended | SRF Expended | Total Expended | Grant Expended | Cash Match | In-kind Expended | SRF Expended | Total Expended | Grant Expended | Cash Match | In-kind Expended | SRF Expended | Total Expended | (III.A.1. thr I.1.) | (III.A.2. thr I.2.) | (III.A.3. thr I.3.) | (III.A.4. thr I.4.) | (III.A.5. thr I.5.) | ( II.A. - IV.A.) | ( II.B. - IV.B.) | ( II.C. - IV.C.) | ( II.D. - IV.D.) | ( II.E. - IV.E.)
[11 empty] | Expended |  |  |  |  | Expended |  |  |  |  | Expended |  |  |  |  | Expended |  |  |  |  | Expended |  |  |  |  | Expended |  |  |  |  | Expended |  |  |  |  | Expended |  |  |  |  | Expended
OBJECTIVE 1 - FEEDLOT MANAGEMENT
SWCD/NRCS/Environmental Services | District Manager | 28 | /hr. | 190 |  |  | 5320 |  | 5320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5320 | 0 | 5320
| Transportation | 0.38 | /mile | 900 |  |  | 342 |  | 342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342 | 0 | 342
EQUIP & Other Funding Programs | [6 empty] | 375000 |  | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 0 | 375000
NFCRWD | Technician | 21 | /hr. | 50 |  |  | 1050 |  | 1050 | [50 empty] | 0 | 0 | 1050 | 0 | 1050
| Transportation | 0.38 | /mile | 150 |  |  | 57 |  | 57 | [50 empty] | 0 | 0 | 57 | 0 | 57
| Adminstrator | 32 | /hr. | 90 |  |  | 2880 |  | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880 | 0 | 2880
| Transportation | 0.38 | /mile | 900 |  |  | 342 |  | 342 | [50 empty] | 0 | 0 | 342 | 0 | 342
Administrative Cost - Tracking & Education |  | 31 | /hr. | 339 | 8000 |  | 3500 |  | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 3500 | 0 | 11500
See Appendix A | Landowner-SRF | [6 empty] | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
OBJECTIVE 1 - TOTAL |  |  |  |  | 8000 | 0 | 388491 | 200000 | 596491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 388491 | 200000 | 596491
OBJECTIVE 2 - BEST MANAGEMENT PRACTICES
SWCD/NRCS/Environmental Services | Saff | 28 | /hr. | 160 |  |  | 4480 |  | 4480 | [50 empty] | 0 | 0 | 4480 | 0 | 4480
| Joint Powers Engineer | 31 | /hr. | 160 |  |  | 4960 |  | 4960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4960 | 0 | 4960
| Transportation | 0.38 | /mile | 1200 |  |  | 456 |  | 456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456 | 0 | 456
EQUIP & Other Funding Programs Plans | [5 empty] | 25000 | 25000 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 50000
NFCRWD | Technician | 21 | /hr. | 165 |  |  | 3465 |  | 3465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3465 | 0 | 3465
| Transportation | 0.38 | /mile | 625 |  |  | 237.5 |  | 237.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237.5 | 0 | 237.5
| Administrator | 32 | /hr. | 250 |  |  | 8000 |  | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 8000
| Transportation | 0.38 | /mile | 1000 |  |  | 380 |  | 380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 0 | 380
Administrative Cost - Tracking & Education |  | 31 | /hr. | 645 | 10000 | 10000 | 10000 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 0 | 30000
Grants for Rain Garden & Water Quality Projects |  |  |  |  | 40000 |  |  |  | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 40000
Landowners SRF Loans | Landowner-SRF | [6 empty] | 22500 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500 | 22500
OBJECTIVE 2 - TOTAL |  |  |  |  | 50000 | 35000 | 56978.5 | 22500 | 164478.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 35000 | 56978.5 | 22500 | 164478.5
OBJECTIVE 3 - SEWAGE UPGRADE
SWCD/NRCS/Evironmental Services | Staff | 28 | /hr. | 160 |  |  | 4480 |  | 4480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4480 | 0 | 4480
| Joint Powers Engineer | 31 | /hr. | 60 |  |  | 1860 |  | 1860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1860 | 0 | 1860
| Transportation | 0.38 | /mile | 1250 |  |  | 475 |  | 475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475 | 0 | 475
NFCRWD | Technician | 21 | /hr. | 125 |  |  | 2625 |  | 2625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2625 | 0 | 2625
| Administrator | 32 | /hr. | 150 |  |  | 4800 |  | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 0 | 4800
Septic Upgrades | Landowner-SRF | [6 empty] | 127500 | 127500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127500 | 127500
Administration Costs - Tracking & Education |  | 31 | /hr. | 323 | 6000 | 4000 | 4000 |  | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 4000 | 4000 | 0 | 14000
OBJECTIVE 3 - TOTAL |  |  |  |  | 6000 | 4000 | 18240 | 127500 | 155740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 4000 | 18240 | 127500 | 155740
OBJECTIVE 4
Monitoring | Lab and other costs |  |  |  | 15000 | 25425 | 25425 |  | 65850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 25425 | 25425 | 0 | 65850
AdministrationCost - Tracking & Education |  | 31 | /hr. | 355 | 6000 | 5000 | 5000 |  | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 5000 | 5000 | 0 | 16000
OBJECTIVE 4 TOTAL |  |  |  |  | 21000 | 30425 | 30425 | 0 | 81850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 | 30425 | 30425 | 0 | 81850
| TOTAL |  |  |  | 85000 | 69425 | 494134.5 | 350000 | 998559.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 69425 | 494134.5 | 350000 | 998559.5