## Title & Info Page
MPCA Quality Assurance Project Plan Checklist p-eao-13b • 5/9/25
This checklist is based on the U.S. Environmental Protection Agency (EPA) Quality Assurace Project Plan (QAPP) Standard (Directive No: CIO 2105-S-02.1). The purpose of this document is to serve as a resource for those charged with developing and reviewing QAPPs.
Checklist items with a triangle in the upper right corner contain comments with additional information. Hover over the cell to view the comment.
If the project does not readily fit in the structure or content described in this checklist and the project is EPA sponsored, reach out to the EPA organization sponsoring the work for guidance.
If a section in this checklist does not apply to the project, still list the heading and note “Not applicable to the scope of the project” under the section title.
Additional Resources
EPA QAPP Standard: | https://www.epa.gov/system/files/documents/2024-04/quality_assurance_project_plan_standard.pdf
QAPP template, QAPP guidance and other resources found on MPCA's Science and data webpage: | https://www.pca.state.mn.us/about-mpca/science-and-data
Email address for QA questions: | qa.questions.mpca@state.mn.us
QAPP Title:
Date of Review:
Reviewer(s):

## Checklist
Quality Assurance Project Plan Checklist
Version: March 2025
|  | Acceptable | Unacceptable | N/A | Comments
A1. Title Page
Document title contains the project name and is identified as "Quality Assurance Project Plan"
Name of organization preparing the QAPP and name of who the QAPP is being prepared for
Date of QAPP preparation and period of applicability (e.g., length of agreement, grant end date)
Revision/version control number
If work is performed under an EPA assistance agreement or EPA contract acquisition, specify the grant, cooperative agreement, contract, and/or task order number as applicable
Interagency Agreement number, title and date of the Memoranda of Understanding, citation of regulatory requirement, or title and date of enforcement or legal agreement as applicable
A2. Approval Page
Dated signatures of MPCA Project and QA staff
If EPA approval is required, include dated signatures from EPA project officer and EPA QA Manager
If third parties (contractors/laboratories) are involved in the project, include dated signatures from third party project manager, QA rep, and other applicable personnel
A3. Table of Contents, Document Format, and Document Control
Table of contents
QAPP format uses titles of each section as outlined in this checklist
Document control is included on every page (title, version number, date, page number)
A4. Project Purpose, Problem Definition, and Background
Identifies other relevant QA planning documents (e.g., a QAPP from an earlier phase in the project, QMPs)
Clearly describes the purpose of the project work, including the problem(s) to be addressed, hypothesis to be tested and intended use(s) of the data
Documents the environmental decision(s) to be made and the level of information needed to ensure decisions are based on sound environmental information
Generally identifies type, quantity, and quality of information needed for the intended use(s) and describes the data acceptance and performance criteria
Cites applicable technical, regulatory, or program-specific quality standards, criteria, or objectives, and conceptual site model(s)
Includes a discussion that directly links the results of the project work to possible actions
Describes or cites historical and background information to give perspective for the project and identifies sources for existing information that will be used
A5. Project Task Description
Describes all tasks to be performed
Describes measurements to be made/data to obtained/products to be produced for each task
Provides work schedule for accomplishment of the tasks
A6. Information/Data Quality Objectives and Performance/Acceptance Criteria
Discusses the project's information/data quality objectives, the performance and/or acceptance criteria needed to meet those objectives, and the information/data quality indicators that will be looked at (i.e. what are the specific standards for the data needed for meeting the project objectives)
If the project includes laboratory analysis, describes performance and acceptance criteria of analytical methods (each matrix, each analyte or analyte group, and concentration level)
Addresses applicable Data Quality Indicators (e.g. precision, accuracy, representative, comparative, completeness, sensitivity, and/or others that may apply) and includes calculations for the indicators
A7. Distribution List
Includes name, email address, organization and title of all individuals who are to implement or otherwise receive the QAPP
If a lab or sub-contractor is involved, includes at least one individual from each in the distribution list
Includes a member of MPCA Environmental Data Quality Unit in the distribution list
A8. Project Organization
Identifies key individuals and describes their roles and responsibilities (e.g., data users, decision makers, technical staff, principal project workers, project QA manager, subcontractors)
Includes those responsible for circulation of the QAPP to the distribution list, the annual QAPP review and overall management of the QAPP
A9. Project QA Manager Independence
Documents how the quality assurance representative acts independently from the rest of the project.
A10. Project Organizational Chart and Communications
Organizational chart includes all individuals included in Section A8 or elsewhere described in the QAPP as having responsibilities directly related to project work
Organizational chart shows lines of authority/reporting responsibilities and lines of communication between and within organizations
Describes communication procedures including timing of communication in detail sufficient for QAPP users to understand their role when communication is necessary
If project is EPA sponsored, describes communication procedures to EPA including elevating discrepancies and QAPP non-conformances
A11. Personnel Training/Certification
Describes any required specialized training or certifications for project personnel and how the training is documented
Identifies individuals responsible and processes in place to ensure personnel performing the project work are qualified, trained, and appropriately experienced
A12. Documents and Records
Identifies documents and records that will be produced (e.g., raw data, field logs, results of QC checks, problems encountered)
Describes or references the management procedures of the documents and records, including the QAPP. Also states who the responsible individuals are
Describes retention schedule and specific location for records (this should align with organization's retention policy)
B1. Identification of Project Environmental Information Operations
Describes in detail the project work to be conducted
States how the project work has been designed to meet the project purpose
States how the project work will satisfy the data quality objectives and performance acceptance criteria as stated in A4 and A6
B2. Methods for Environmental Information Acquisition
Describes in detail or references methods and procedures used for the acquisition of data
If a Standard Operating Procedure (SOP) is being referenced, includes the name, number, version/revision number and section/page numbers (if applicable) of the SOP
If an SOP is being referenced, includes the SOP document within this section, as an appendix or available via an in-text link
Identifies any planned modifications to SOPs that are likely to occur during the project and the individual responsible for such updates
B2.1 If the project includes field work…
Describes or references procedures for all activities, including sample collection procedures, information derived from tools, instruments and observational results
Documents maximum holding times for sample extraction/analysis, sample selection, preparation of sample containers, sample volumes, preservation methods, and procedures for sample handling and custody
B2.2 If the project includes laboratory analysis…
Identifies analytical methods by number/identifier, version/revision date and regulatory citation (Example: EPA 351.2 Rev. 2 1993).
States requested lab turnaround time
States that electronic data deliverables (EDDs) provided by the lab must be in the lab_mn format
References or includes SOPs that address when a non-compliance or failure in the analysis or samples occurs. Includes who is responsible for the corrective action and how to determine the effectiveness of the corrective action
B2.3 If the project includes compiling or obtaining data from existing sources…
Describes the data to be obtained, collection process and intended use of the data
Describes the criteria for acceptance and evaluation of the secondary data
B2.4 If the project includes environmental technology…
Identifies whether the technology is being used for pollution prevention, contamination containment, storage or remediation
Explains the physical factors or processes gathered using environmental technologies, along with the systems, devices and parts that are used to measure or remove pollutants and/or prevent them from entering the environment
B3. Integrity of Environmental Information
Describes or cites the procedures for ensuring the integrity of the project work
If the project includes field sampling, describes or cites the procedures for sample handling and custody. Includes or references examples of sample labels and chain of custody forms
If the project work includes laboratory analysis, identifies each lab to be used including a back-up lab. Includes the processes for ensuring that the laboratory maintains current accreditation for the analytes and matrices applicable to the scope of the project
B4. Quality Control
Describes the Quality Control (QC) procedures needed for the project work to meet project/quality objective and performance/acceptance criteria
Describes or cites the frequency of each QC activity, acceptance criteria, corrective actions, and how the effectiveness of the corrective actions will be determined. Includes descriptions or references to the procedures to be used to calculate applicable statistics
Describes or references the sensitivity of the instruments used for analysis (Reporting Limits, Method Detection Limits, Limits of Quantitation, etc.)
B5. Instruments/Equipment Calibration, Testing, Inspection, and Maintenance
Lists instruments/equipment (e.g., tools, gauges, pumps) needs
Describes procedures and documentation activities to ensure instruments/equipment are available and in working order
Includes descriptions or references for procedures and documentation activities on how instruments and equipment will be tested, inspected, and maintained
Notes availability and location of critical spare parts
Identifies how calibration will be conducted, documented and traceable to the specific piece of equipment (including frequency and acceptance standards)
B6. Inspection/Acceptance of Supplies and Services
Describes or references the procedures for how supplies and services are inspected and accepted (includes who is responsible for this activity)
If the project may involve the addition of other parties (contractors, subcontractors, laboratories, subgrantees, etc.) documents how these parties will be selected, who is responsible for that decision, and what requirements are to be considered
B7. Environmental Information Management
Describes data management process from its generation to final use or storage (trace the path of the information from field to laboratory to office to database)
Describes or references the standard record-keeping procedures, the document control system, and the approach used for information storage and retrieval
Describes the process for detecting and correcting errors and for preventing loss of data during data entry, reduction and reporting. If there are checklists or forms used in this process, include them in an appendix
Describes or references all procedures to process, compile, and analyze the data obtained from project work
Describes or references any required computer hardware/software and address any specific performance requirements
C1. Assessments & Response Actions
Describes required number, frequency, & type of assessments
Identifies individual(s) performing the assessments and ensures no conflict of interest by demonstrating assessors are independent of the project work
Addresses how assessment findings, non-conformances, and corrective actions will be developed, documented and tracked to ensure completion and communication of assessment results to management and/or the sponsoring organization
Identifies individuals responsible for response actions and how they will be documented and reported (response actions address findings, corrective actions and non-conformances identified from the assessments)
C2. Oversight and Reports to Management
Describes oversight activities that ensure response actions and reporting mechanisms are in place to capture project status and any QA issues that arise and identifies those responsible for oversight activities
Identifies all reports to management and describes the content of each report, the responsible individuals for the reports, how the reports will transmitted and to whom
D1. Environmental Information Review
Describes/cites the procedures for data verification and data validation. Includes who will conduct these activities, criteria for accepting, rejecting, and qualifying data, and how these activities will be documented and communicated
Describes/cites the procedures for data quality assessment activities. Includes who will conduct these activities, criteria for accepting, rejecting, and qualifying data, and how these activities will be documented and communicated
Includes how the data quality objectives and acceptance criteria outlined in A6 will be utilized in the review process
D2. Usability Determination
Describes the process and individuals responsible for determining whether the data is useable for its intended purpose
Describes how the usability determination will be documented and how any known or anticipated limitations on the use of the data will be communicated to data users or decision-makers
Notes
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If the project does not readily fit in the structure or content described in this checklist and the project is EPA sponsored, reach out to the EPA organization sponsoring the work for guidance.
Note on B18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The title can be a shortened version of the title. Example: "MPCA CPRG QAPP" instead of "Quality Assurance Project Plan for Minnesota Pollution Control Agency Green House Gas Inventory and Options Identification Phase of the Climate Pollution Reduction Grants Program"
Note on B27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A table format often works well for this section
Note on B34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: General overall acceptance criteria for precision and accuracy can be found in guidance documents located on the MPCA Science and Data Webpage (Science and data ¦ Minnesota Pollution Control Agency (state.mn.us) Definitions of the data quality indicators can be found on page 8 of the QAPP Template https://www.pca.state.mn.us/sites/default/files/p-eao2-13a.docx
Note on B35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A table format often works well for this section
Note on B40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Unless otherwise specified, using job titles + organization name in this section vs. specific individual names is recommended, so the QAPP does not need to be revised is there is staff turnover.
Note on B43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Example language for when the QA representative is from the MPCA Environmental Data Quality Unit: "The MPCA QA Coordinator is employed by the MPCA’s Environmental Analysis & Outcomes (EAO) Division Environmental Data Quality Section, which is in a separate (insert Division or Section) from MPCA’s (insert Division or Section). The Manager of the Data Quality Section reports directly to the EAO Division Director, who according to the MPCA’s QMP, acts as the MPCA Quality Assurance Director.”
Note on B61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The acquisition of data includes collection, production, evaluation, design, construction, operation, or application of environmental technology
Note on B73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Existing sources may include databases, software applications, decision support tools, websites, existing literature, etc.
Note on B81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Include procedures such as use of field logs, packaging, transportation and storage.
Note on B84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For projects involving field sampling, measurements, and laboratory analysis, QC activities may include the use of blanks, duplicates, matrix spikes, laboratory control samples and surrogates. For projects using existing data, QC activities include the use of systematic review, independent secondary review of studies in the open literature, and QC of constructed databases or spreadsheets. For projects using models or modeling, QC activities include model calibration and model validation.
Note on B85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Statistics may include precision, bias, accuracy, etc.
Note on B94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Supplies may include: spare parts, standards, sample bottles, calibration gauges, reagents, hoses, deionized water, potable water and electronic data storage media
Note on B101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ex. electronic data deliverables submitted to the MPCA must be in the lab_mn format. Include the procedures to demonstrate acceptability of the hardware/software configuration required, document programmatic requirements for the lab_mn EDD submittal and describe who will be receiving the PDFs. The individual shall be included in any relevant project COCs.
Note on B102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assessments ensure that the QAPP is implemented as approved. Response actions address findings, corrective actions and non-conformances identified from the assessments.
Note on B103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assessment activities may include audits, performance evaluations, management reviews, peer reviews, inspections, surveillances, or readiness reviews (including competency assessment, pre-award assessment of proposal, or technical assessment), peer consultations, product reviews (e.g., data inspection, software testing, pre-dissemination reviews, or review of contractor deliverables).
Note on B105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Documentation may include reports, memos, and/or other formal communication.
Note on B106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Response actions may include memos, notifications, corrective actions and timelines for follow-up assessments.
Note on B109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Report distribution should include to the project managers, QA staff and the EPA organization sponsoring the work, if applicable
Note on B111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Definitions: Data verification: The process of evaluating the completeness, correctness, and conformance/compliance of a specific data set against the method, procedural, or contractual requirements. Data validation: An analyte- and sample-specific process that extends the evaluation of data beyond method, procedural, or contractual compliance (i.e., data verification) to determine the analytical quality of a specific data set.
Note on B112: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data quality assessment definition: the scientific and statistical evaluation of data to determine if the data obtained from project work are of the right type, quality, and quantity to support their intended use. Occurs after the project work phase is completed.

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only